## RACI Matrix (Simplified)
RACI LEGEND:
R = Responsible (does the work)
A = Accountable (final decision authority)
C = Consulted (provides input before decision)
I = Informed (kept updated on progress)
# | Work Package / Task | Esri SA | Lithodat | SGS | Comments
0 | TENDER PREPARATION
0.1 | Tender response preparation and submission | A | R | I
0.2 | Partnership agreement finalization | A | C | I
0.3 | Saudi Ministry of Investment registration (foreign bidders) | A | I | I
0.4 | Proposal and pricing | A | C | I
1 | PROJECT INITIATION & PLANNING
1.1 | Saudi legal and contract management | A | I | C
1.2 | Saudization and local content compliance plan | A | C | C
1.3 | Project research - SGS geological data landscape | C | A | C
1.4 | Requirements validation workshop | R | A | C
1.5 | Project management plan development | A | C | C
1.6 | Cyber Security Management Plan | A | C | C
1.7 | Quality Management Plan - Geological Data | C | A | C
1.8 | Environmental Health and Safety (EHS) Plan | A | C | C
2 | DATA ARCHITECTURE & PREPARATION
2.1 | Data modeling and data dictionary definition | C | A | C
2.2 | New geology datatype model development (if required) | C | A | C
2.3 | LithoBuild - SGS-specific database creation | C | A | I
2.4 | Database hosting infrastructure setup | A | C | I
2.5 | Security testing | A | R | I
2.6 | LithoClean - Data cleaning and ETL preparation | R | A | I
2.7 | Staged data migration by datatype | C | A | C
2.8 | Geologist quality review and validation | I | A | C
3 | AI/ML DEVELOPMENT FOR MINERAL EXPLORATION
3.1 | Mineral prospectivity modeling and exploration targeting | C | A | C
3.2 | Geological knowledge assistant (LLM + semantic search) | C | A | I
3.3 | Geochemical data processing and pattern recognition | C | A | C
3.4 | Automated quality control and anomaly detection | C | A | I
3.5 | Geospatial analysis and geological province mapping | C | A | C
3.6 | Environmental and social impact analytics (Phase 4) | C | A | C
4 | SYSTEM CONFIGURATION & INTEGRATION
4.1 | ArcGIS configuration and environmental setup | A | C | I
4.2 | API database integration with ArcGIS | A | C | I
4.3 | Integration testing (ArcGIS + LithoSurfer) | R | A | I
5 | ANALYTICS VISUALIZATION & AI ENABLEMENT
5.1 | LithoSurfer visualizations rebuild/migration to ArcGIS | C | A | I
5.2 | ArcGIS out-of-the-box tools - geology-specific customization | A | C | C
5.3 | Advanced analytical tools implementation | C | A | C
6 | TESTING & ACCEPTANCE
6.1 | Integration and performance testing | R | R | I
6.2 | User Acceptance Testing (UAT) with SGS | R | R | A
6.3 | Security and penetration testing | A | C | I
6.4 | Final acceptance testing | C | C | A
7 | TRAINING & KNOWLEDGE TRANSFER
7.1 | End-user training (SGS geologists) | C | A | R
7.2 | Administrator training (SGS IT staff) | A | C | R
7.3 | User guide and documentation handover | R | R | I
7.4 | Technical documentation (architecture APIs) | R | A | I
8 | DEPLOYMENT & GO-LIVE
8.1 | ArcGIS Enterprise production deployment | A | C | I
8.2 | LithoSurfer production deployment | C | A | I
8.3 | Production database cutover | R | A | C
8.4 | Go-live support and issue resolution (hypercare period) | R | R | I
9 | SUPPORT & TRANSITION
9.1 | Performance monitoring setup | A | C | I
9.2 | Support model handoff to operations teams | R | R | C
9.3 | Operational runbooks and procedures | R | R | I
9.4 | Final project acceptance and sign-off | C | I | A
9.5 | Ongoing Support / Contract extensions | R | R | C
10 | PROJECT MANAGEMENT & GOVERNANCE
10.1 | Lithodat scope - technical deliverables tracking | C | A | I
10.2 | Overall project management and governance | A | C | C
10.3 | Status reporting to SGS | A | C | I

## Summary Dashboard
GDAC-SA Partnership RACI Matrix (Simplified) - Summary
Project | GDAC-SA Advanced Analytics Platform
Partnership | ESRI Saudi Arabia (Prime) + Lithodat (Subcontractor)
Document | Simplified Responsibility Assignment Matrix (RACI)
Version | 1.0 - 2025-12-30
Work Package Summary
WP# | Phase | Task Count | ESRI Accountable | Lithodat Accountable | SGS Accountable | Joint
0 | TENDER PREPARATION | 4 | 4 | 0 | 0 | 1
1 | PROJECT INITIATION & PLANNING | 8 | 5 | 3 | 0 | 1
2 | DATA ARCHITECTURE & PREPARATION | 8 | 2 | 6 | 0 | 2
3 | AI/ML DEVELOPMENT FOR MINERAL EXPLORATION | 6 | 0 | 6 | 0 | 0
4 | SYSTEM CONFIGURATION & INTEGRATION | 3 | 2 | 1 | 0 | 1
5 | ANALYTICS VISUALIZATION & AI ENABLEMENT | 3 | 1 | 2 | 0 | 0
6 | TESTING & ACCEPTANCE | 4 | 1 | 0 | 2 | 2
7 | TRAINING & KNOWLEDGE TRANSFER | 4 | 1 | 2 | 0 | 4
8 | DEPLOYMENT & GO-LIVE | 4 | 1 | 2 | 0 | 2
9 | SUPPORT & TRANSITION | 5 | 1 | 0 | 1 | 3
10 | PROJECT MANAGEMENT & GOVERNANCE | 3 | 2 | 1 | 0 | 0
TOTAL |  | 52 | 20 | 23 | 3 | 16
Accountable Task Distribution
Party | Accountable Tasks | Percentage | Primary Focus
ESRI SA | 20 | 38.5% | Commercial, Legal, ArcGIS, Client Management
Lithodat | 23 | 44.2% | Technical, Geological Data, AI/ML, Training
SGS | 3 | 5.8% | Acceptance, Testing, Operational Decisions
Joint Tasks | 16 | 30.8% | Collaborative efforts across parties

## Legend & Guide
RACI Matrix Legend & User Guide (Simplified Version)
RACI Roles Explained
Role | Name | Definition | Color
R | Responsible | Does the work to complete the task | Light Green
A | Accountable | Final decision authority - ONE per task | Light Orange
C | Consulted | Provides input before decision | Light Blue
I | Informed | Kept updated on progress | Very Light Green
S | Support | Provides supporting assistance | Light Peach
RACI Best Practices
1. Each task MUST have exactly ONE Accountable (A) party
2. Multiple parties can be Responsible (R) for doing the work
3. Consulted (C) parties provide input BEFORE decisions are made
4. Informed (I) parties are updated AFTER decisions are made
5. Avoid "RA" dual accountability - split into separate A and R
6. Keep RACI assignments simple - too many roles creates confusion
Stakeholder Descriptions
Party | Role in Project | Primary Responsibilities
ESRI SA | Prime Contractor | Commercial, Legal, ArcGIS Infrastructure, Client Relationship, Saudi Compliance
Lithodat | Technical Subcontractor | Geological Data Systems, AI/ML Development, LithoSurfer, Training, Quality
SGS | Client/End User | Requirements, Acceptance Testing, Operational Handover, Final Sign-off
Comments Column Usage Guide
The Comments column (yellow background) is for:
• Documenting decisions made during partnership discussions
• Recording clarifications or assumptions
• Noting dependencies or prerequisites
• Tracking status updates or blockers
• Linking to related documents or meetings
• Highlighting risks or concerns
Example comments:
• "Pending ESRI confirmation on ArcGIS Enterprise license count"
• "Requires SGS data access approval before start"
• "Wayne Noble allocated 0.5 FTE for 3 months"
• "Decision: Hybrid architecture approved 2025-12-30"